## Product Backlog
WBGT CrewSafe SG — Prioritised Product Backlog
ID | Priority (MoSCoW) | Feature / User Story | Story Points | Implementation Technologies | Acceptance Summary | Sprint
US-19 | Must | Prepare prioritised backlog, high-level use-case diagram and UI prototype screens | 5 | Figma / AI design tools; documentation | Backlog, use-case diagram and navigable mockups accepted by advisor | 0
US-20 | Must | Spike: confirm NEA WBGT/lightning feasibility and cache demo fixtures | 3 | NEA data.gov.sg APIs; fixture cache | Live pull demonstrated; dated fixtures cached for offline demo | 0
US-01 | Must | Authenticate and see only my assigned site | 5 | Web (React, TypeScript); Mobile (React Native, Expo); Backend (Spring Boot, Spring Security, JWT); PostgreSQL | RBAC and negative authorization tests pass | 1
US-02 | Must | Create a shift with workers, tasks and intensity | 8 | Web (React, MUI); Backend (Spring Boot, Spring Data JPA); PostgreSQL | Shift validation and assignments persist | 1
US-03 | Must | Worker views shift and submits readiness flags | 5 | Mobile (React Native, Expo); Backend (Spring Boot); PostgreSQL | Only assigned worker can submit; no medical free text | 1
US-04 | Must | Ingest and store WBGT / weather with freshness | 8 | Backend (Spring Boot scheduler); NEA data.gov.sg APIs; PostgreSQL | Live and fixture modes work; duplicate ingestion safe | 1
US-04L | Must | Lightning stop-work warning shown above WBGT | 5 | Backend (Spring Boot scheduler); NEA lightning observation API; React · React Native | Risk state clear/advisory/stop-work; warning atop WBGT; overrides heat plan | 1
US-05 | Must | Supervisor sees current conditions and active shift context | 5 | Web (React, Chart.js); Backend (Spring Boot) | Web view uses shared backend and shows freshness | 1
US-21 | Must | Provision cloud staging infrastructure and secrets management | 5 | AWS Amplify Hosting (S3 + CloudFront); ECS on Fargate; RDS for PostgreSQL; Secrets Manager | Web + mobile reach one deployed backend; no secrets in source | 1
US-22 | Must | Establish CI pipeline skeleton (build, unit tests, SAST, secret scan) | 5 | GitHub Actions; SAST; secret scanning | PR triggers build, tests and scans; main branch protected | 1
US-23 | Should | Baseline observability: health checks, correlation IDs, structured logs | 3 | Backend (Spring Boot Actuator); Amazon CloudWatch + X-Ray | Health endpoints live; correlation IDs traced end-to-end | 1
US-06 | Must | System forecasts 30 / 60-minute WBGT | 8 | Python ML service (FastAPI, pandas, scikit-learn / XGBoost, time-series regression) | Baselines measured; versioned prediction returned | 2
US-07 | Must | Evaluate the correct deterministic policy actions | 8 | Backend (Java 21 deterministic rules engine); PostgreSQL policy config | Boundary and mixed-worker tests pass | 2
US-08 | Must | Supervisor receives an explainable agent draft plan | 8 | Agentic AI (tool-calling LLM via Spring Boot adapter, JSON-schema guarded tools) | No unsupported actions; policy / model references shown | 2
US-09 | Must | Supervisor approves, edits or rejects a plan | 5 | Web (React); Backend (Spring Boot) | Draft and final versions retained; authorization enforced | 2
US-10 | Must | Worker receives and acknowledges an approved action | 8 | Mobile (React Native); Backend (idempotency keys); PostgreSQL | Only affected workers see it; idempotency works | 2
US-11 | Must | Worker logs rest / hydration or raises a concern | 5 | Mobile (React Native); Backend (Spring Boot) | Status updates in supervisor view | 2
US-12 | Must | Supervisor monitors pending, late and completed actions | 5 | Web (React, Chart.js); Backend (Spring Boot) | Live state and alert count match backend records | 2
US-24 | Must | Safety manager configures and versions the active heat policy | 5 | Web (React); Backend (Spring Boot); PostgreSQL policy_version | Versioned catalogue with source & effective date; recommendations cite version | 2
US-27 | Must | Complete DevSecOps pipeline (dependency + container scan, auto staging deploy, smoke tests) | 5 | GitHub Actions; dependency scan; container scan; staging deploy | Pipeline scans, deploys staging and runs smoke tests | 2
US-13 | Must | Manager views compliance and response-time charts | 8 | Web (React, Chart.js); Backend aggregation queries | Metrics verified against seeded expected values | 3
US-14 | Must | Manager views forecast accuracy and fallback status | 5 | Web (Chart.js); Python ML evaluation metrics; Backend | Metrics match evaluation artifact | 3
US-15 | Must | Manager exports the audit timeline | 5 | Backend (CSV / PDF export); Web; PostgreSQL append-only audit | Export contains trace IDs, actors, rules and decisions | 3
US-16 | Must | Safe degraded behaviour during dependency failure | 8 | Backend fallback adapters (NEA / ML / LLM); persistence forecast | NEA, ML and LLM failure scenarios pass | 3
US-17 | Should | In-app reminder for an unacknowledged approved action | 3 | Backend (scheduler); Mobile (in-app notification) | Reminder cannot alter instruction | 3
US-25 | Should | Show readiness-check freshness and missing checks | 3 | Mobile + Web (React); Backend (Spring Boot) | Stale or missing readiness flagged to supervisor | 3
US-26 | Should | STPA-derived agent guardrail verification (allowlist + approval gate) | 5 | Agentic AI adapter; Backend validation; test harness | Unsupported-action rate zero; approval-gate bypass blocked and audited | 3
US-28 | Must | Security testing suite and remediation evidence | 8 | Authz / injection / XSS / prompt-injection / audit-tamper tests; dependency & container review | Findings, severity, remediation and re-test documented; no unresolved high/critical | 3
US-29 | Should | ML model card with SHAP explainability and forecast-reliability | 3 | Python ML (SHAP); model-card document | Card includes SHAP drivers, calibration and per-band error | 3
US-30 | Should | Admin manages users, roles, sites and integrations | 5 | Web (React); Backend (Spring Security); PostgreSQL | Admin CRUD with RBAC; every change audited | 3
US-31 | Should | Accessibility and performance checks (WCAG 2.1 AA basics; p95 latency) | 3 | Web + Mobile; axe / Lighthouse; load test | WCAG AA basics met; read p95 <1s, write p95 <2s | 3
US-18 | Could | Worker views an approved instruction in another language | 5 | Agentic AI (human-approved LLM template); Mobile (React Native) | Human-approved template only | Stretch
US-32 | Could | QR check-in at a simulated rest zone | 3 | Mobile (Expo Camera); Backend | Scan logs rest at zone; event audited | Stretch
US-33 | Could | Multi-site management view | 5 | Web (React); Backend (Spring Boot) | Manager switches and compares multiple sites | Stretch
US-34 | Could | Supervisor-entered local WBGT reading with source & timestamp | 3 | Web + Mobile; Backend (Spring Boot) | Manual reading stored with source/time; no station-equivalence claim | Stretch
US-35 | Could | Push notifications via Firebase Cloud Messaging | 5 | Mobile (Expo + FCM); Backend | Approved action pushes to worker device | Stretch
Sprint schedule (per AD Project Instructions): Sprint 0 = Week 1 (Inception & Requirements) · Sprint 1 = Week 2 (Design & Prototyping / infrastructure) · Sprint 2 = Week 3 (Development / MVP + DevSecOps) · Sprint 3 = Week 4 (Development, quality, security, demo) · Stretch = post-MVP, only after all Must stories pass.

## Features
Features — Proposed Features & Implementation Technologies
Feature (use case / user story) | Additional Details (Implementation Technologies)
Authenticate & site-scoped access | Web (React, TS) + Mobile (React Native) + Backend (Spring Boot, Spring Security, JWT, PostgreSQL)
Configure shift, tasks & assignments | Web (React, MUI), Backend (Spring Boot, Spring Data JPA, PostgreSQL)
Complete worker readiness check | Mobile (React Native, Expo), Backend (Spring Boot, PostgreSQL)
Ingest WBGT & weather with freshness | Backend (Spring Boot scheduler), NEA data.gov.sg APIs, PostgreSQL
Lightning warning above WBGT (stop-work) | Backend (Spring Boot), NEA lightning observation API, React + React Native
View current & forecast risk (live conditions) | Web (React, Chart.js), Backend (Spring Boot)
Forecast 30 / 60-minute WBGT | Python ML (FastAPI, pandas, scikit-learn / XGBoost, time-series)
Evaluate deterministic heat policy | Backend (Java 21 rules engine, PostgreSQL policy config)
Configure & version heat policy | Web (React), Backend (Spring Boot), PostgreSQL policy_version
Generate explainable agent draft plan | Agentic AI (tool-calling LLM via backend adapter, JSON-schema tools)
Agent guardrail verification (STPA, allowlist, approval gate) | Agentic AI adapter, Backend validation, test harness
Approve / edit / reject plan | Web (React), Backend (Spring Boot)
Dispatch & acknowledge worker action | Mobile (React Native), Backend (idempotency, PostgreSQL)
Log rest / hydration & raise safety concern | Mobile (React Native), Backend (Spring Boot)
Readiness-check freshness & missing-check indicators | Mobile + Web (React), Backend (Spring Boot)
Monitor completion (live status board) | Web (React, Chart.js), Backend (Spring Boot)
Compliance & response-time dashboard | Web (React, Chart.js), Backend aggregation
Model-performance dashboard | Web (Chart.js), Python ML metrics, Backend
ML model card (SHAP explainability, reliability) | Python ML (SHAP), model-card documentation
Export audit timeline (CSV / PDF) | Backend (export service), Web, PostgreSQL append-only audit
Graceful degraded mode | Backend fallback adapters (NEA / ML / LLM)
Observability & health monitoring | Backend (Spring Boot Actuator), CloudWatch + X-Ray
Security testing & remediation evidence | OWASP-style tests (authz, injection, XSS, prompt-injection, audit-tamper), dependency & container scanning
Accessibility & performance | Web + Mobile, axe / Lighthouse, load test (WCAG 2.1 AA basics; p95 latency)
Admin: users, roles, sites & integrations | Web (React), Backend (Spring Security), PostgreSQL
[Stretch] Multilingual instruction template | Agentic AI (human-approved LLM template), Mobile
[Stretch] QR rest-zone check-in | Mobile (Expo Camera), Backend
[Stretch] Multi-site management view | Web (React), Backend (Spring Boot)
[Stretch] Supervisor-entered local WBGT reading | Web + Mobile, Backend (Spring Boot)
[Stretch] Push notifications (Firebase Cloud Messaging) | Mobile (Expo + FCM), Backend
[Cross-cutting] Cloud deployment | AWS: Terraform infra, ECS on Fargate, RDS for PostgreSQL, S3, Secrets Manager
[Cross-cutting] DevSecOps pipeline | GitHub Actions CI/CD, SAST + secret scan, dependency & container scanning

## Business Process
Business Process — Heat-Safety Operations Workflow
Actor | Features
Core observe → decide → approve → dispatch → acknowledge → audit loop
NEA Weather Service | Ingest WBGT, weather & lightning (system-triggered)
System (Lightning) | Classify lightning risk; raise stop-work warning above WBGT
System (ML) | Forecast 30 / 60-minute WBGT
System (Policy) | Evaluate deterministic heat policy
System (Agent) | Draft explainable intervention plan
Site Supervisor | Review & approve / edit / reject plan
Site Supervisor | Configure shift & tasks
Site Supervisor | Monitor current & forecast risk
Site Supervisor | Monitor completion & send approved reminder
Outdoor Worker | Receive lightning stop-work alert & seek shelter
Outdoor Worker | Complete readiness check
Outdoor Worker | Receive & acknowledge action
Outdoor Worker | Log rest / hydration
Outdoor Worker | Raise safety concern
Oversight & governance
Safety Manager | Configure policy & users
Safety Manager | View dashboards & audit / export timeline

## Technologies
Architecture-Centric Features — Technology Stack
Layer | Technology | Purpose in WBGT CrewSafe SG
Web app | React, TypeScript, Vite, Material UI, Chart.js | Supervisor / manager / admin console, dashboards, approval workflow
Mobile app | React Native, Expo, TypeScript | Worker readiness, instructions, acknowledgement, rest / hydration logs
Shared backend | Java 21, Spring Boot, Spring Security, Spring Data JPA | System of record, RBAC, policy engine host, audit
Machine learning | Python, FastAPI, pandas, scikit-learn, XGBoost | 30 / 60-minute WBGT time-series forecasting service (internal)
Agentic AI | Tool-calling LLM via backend adapter, JSON schemas | Draft prioritised plans from guarded, authorised tools only
Database | PostgreSQL | Users, sites, shifts, observations, recommendations, append-only audit
API contract | OpenAPI 3, REST /api/v1 | Contract between clients and shared backend
Cloud | AWS infra with terraform, Amazon ECS on Fargate, Amazon RDS for PostgreSQL, Amazon S3, AWS Secrets Manager | Hosting for web, backend, internal ML service and database
Observability | Structured JSON logs, correlation IDs, Amazon CloudWatch + AWS X-Ray | Health checks, traceability, integration-failure metrics
DevSecOps | GitHub Actions, SAST, secret / dependency / container scanning | CI/CD with automated tests and security remediation evidence

## Project Status
Project Status Report (C = Completed · I = In Progress · blank = Not started)
Feature | Implementation Technologies | Sprint | Requirements | Development | Integration Testing | Deployed to Cloud
Authenticate & site-scoped access | Web + Mobile + Backend, PostgreSQL | 1 | C | C | I
Configure shift, tasks & assignments | Web, Backend, PostgreSQL | 1 | C | I
Complete worker readiness check | Mobile, Backend, PostgreSQL | 1 | C | I
Ingest WBGT & weather with freshness | Backend, NEA APIs, PostgreSQL | 1 | C | C
Lightning warning above WBGT | Backend, NEA lightning API, Web + Mobile | 1 | C | I
View current & forecast risk | Web (Chart.js), Backend | 1 | C
Provision cloud staging & secrets | AWS Amplify / ECS / RDS / Secrets Manager | 1 | C | I
CI pipeline skeleton (build/test/SAST/secret) | GitHub Actions | 1 | C | I
Observability (health, correlation IDs, logs) | Backend Actuator, CloudWatch + X-Ray | 1 | C
Forecast 30 / 60-minute WBGT | Python ML (FastAPI, XGBoost) | 2 | C
Evaluate deterministic heat policy | Backend rules engine | 2 | C
Configure & version heat policy | Web, Backend, PostgreSQL | 2 | C
Generate explainable agent draft plan | Agentic AI (LLM adapter) | 2
Approve / edit / reject plan | Web, Backend | 2
Dispatch & acknowledge worker action | Mobile, Backend | 2
Log rest / hydration & raise concern | Mobile, Backend | 2
Monitor completion (live status) | Web, Backend | 2
Complete DevSecOps pipeline (dep/container scan, staging deploy) | GitHub Actions | 2
Compliance & response-time dashboard | Web (Chart.js), Backend | 3
Model-performance dashboard | Web, Python ML metrics | 3
Export audit timeline | Backend (CSV/PDF), Web | 3
Graceful degraded mode | Backend fallback adapters | 3
Security testing & remediation | OWASP-style tests, dependency & container scan | 3
ML model card (SHAP, reliability) | Python ML (SHAP), documentation | 3
Admin: users, roles, sites & integrations | Web, Backend (Spring Security) | 3
Accessibility & performance checks | axe / Lighthouse, load test | 3