## Product Backlog
ComplyDesk — Product Backlog (SME Onboarding & AML Compliance Copilot)
71 features across 11 epics · Prioritised by MoSCoW → Business Value → effort · Pillars: Mobile · Web · ML · Agentic AI · Data Viz · Backend · DevSecOps
ID | Epic | User Story | Pillar | Technology | MoSCoW | Business Value (1-5) | Story Points | Target Sprint | Acceptance Criteria | Status
CD-001 | A. Auth & Access | As a user, I can log in securely so that only authorised staff access the system | Backend | Spring Security, JWT | Must | 5 | 3 | Sprint 1 | Valid creds issue JWT; invalid rejected; token expires | To Do
CD-007 | B. Onboarding & KYC | As an SME applicant, I can self-register on mobile so that I can start onboarding | Mobile | React Native, Spring Boot | Must | 5 | 3 | Sprint 1 | Account created; email verified | To Do
CD-030 | D. Monitoring & ML | As an analyst, the risk score + reason codes appear in the case so that decisions are informed | Web / ML | React, FastAPI | Must | 5 | 3 | Sprint 3 | Score & reasons render in case view | To Do
CD-035 | E. Agentic AI Copilot | As the agent, I can call the ML risk model as a tool so that recommendations use the score | Agentic AI | Tool binding | Must | 5 | 3 | Sprint 3 | Agent invokes model & uses result | To Do
CD-044 | F. STR Reporting | As an analyst, I generate an STR draft from a case so that filing is streamlined | Backend / Agentic AI | Spring Boot, LLM | Must | 5 | 3 | Sprint 3 | STR draft created from case data | To Do
CD-045 | F. STR Reporting | As an MLRO, I review & approve an STR so that filing is controlled | Web / Backend | React | Must | 5 | 3 | Sprint 3 | Approve/reject recorded; locked after approval | To Do
CD-002 | A. Auth & Access | As an admin, I can assign roles (Analyst/MLRO/Admin/SME) so that access is least-privilege | Backend | Spring Security roles | Must | 5 | 5 | Sprint 1 | Each role sees only permitted screens/APIs | To Do
CD-008 | B. Onboarding & KYC | As an SME applicant, I can upload KYC documents (ID, ACRA biz reg) so that identity is verified | Mobile | React Native, S3 | Must | 5 | 5 | Sprint 1 | Files upload to secure storage; listed in case | To Do
CD-016 | C. Case & Alert Mgmt | As an analyst, I see an alert worklist so that I can triage efficiently | Web | React, Spring Boot | Must | 5 | 5 | Sprint 2 | Alerts listed with risk, age, status; sortable | To Do
CD-017 | C. Case & Alert Mgmt | As an analyst, I open a case detail (customer + transactions) so that I can investigate | Web | React | Must | 5 | 5 | Sprint 2 | Case shows profile, txns, risk, history | To Do
CD-019 | C. Case & Alert Mgmt | As an analyst, case status follows a workflow (Open→Investigating→Escalated→Closed) so that lifecycle is controlled | Backend | State machine | Must | 5 | 5 | Sprint 2 | Only valid transitions allowed; audited | To Do
CD-025 | D. Monitoring & ML | As a team, we generate/ingest synthetic transaction data so that we can train & demo without real data | ML / Backend | AMLSim, Python | Must | 5 | 5 | Sprint 1 | Labelled synthetic dataset loaded | To Do
CD-026 | D. Monitoring & ML | As the system, rules raise alerts (thresholds, structuring, velocity) so that known patterns are caught | Backend | Rules engine | Must | 5 | 5 | Sprint 2 | Rule breach creates alert with reason | To Do
CD-028 | D. Monitoring & ML | As an analyst, each alert shows explainability (SHAP reasons) so that I trust the score | ML | SHAP | Must | 5 | 5 | Sprint 3 | Top contributing features shown per alert | To Do
CD-037 | E. Agentic AI Copilot | As an analyst, the agent drafts an STR narrative so that write-up time drops | Agentic AI | LLM | Must | 5 | 5 | Sprint 3 | Draft narrative generated from case | To Do
CD-038 | E. Agentic AI Copilot | As an analyst, the agent recommends a disposition (escalate/close) so that next steps are clear | Agentic AI | LLM | Must | 5 | 5 | Sprint 3 | Recommendation with rationale shown | To Do
CD-039 | E. Agentic AI Copilot | As an MLRO, every agent action pauses for human approval so that AI never acts alone | Agentic AI / Backend | LangGraph HITL | Must | 5 | 5 | Sprint 3 | No mutation without explicit approval | To Do
CD-048 | G. Analytics Dashboard | As a manager, I see a KPI dashboard (alerts, false-positive rate, ageing) so that I monitor operations | Data Viz | React, Chart.js | Must | 5 | 5 | Sprint 3 | Live KPIs render from backend | To Do
CD-057 | I. Audit & Privacy | As an auditor, all state changes write an immutable audit trail so that actions are accountable | Backend | Audit events, PostgreSQL | Must | 5 | 5 | Sprint 2 | Every change logged w/ actor/time | To Do
CD-063 | K. DevSecOps & Cloud | As a team, a CI/CD pipeline builds/tests/deploys so that delivery is automated | DevSecOps | GitHub Actions | Must | 5 | 5 | Sprint 2 | Push triggers build+test+deploy | To Do
CD-065 | K. DevSecOps & Cloud | As a team, features deploy to cloud so that the brief's cloud requirement is met | DevSecOps | AWS App Runner, RDS, S3 | Must | 5 | 5 | Sprint 2 | App reachable on cloud URL | To Do
CD-027 | D. Monitoring & ML | As the system, an ML model scores transaction risk so that suspicious activity is prioritised | ML | XGBoost, FastAPI | Must | 5 | 8 | Sprint 2 | Score 0-1 returned per transaction/customer | To Do
CD-034 | E. Agentic AI Copilot | As an analyst, an agent gathers case context (customer, history, transactions) so that investigation is faster | Agentic AI | LangGraph, LLM | Must | 5 | 8 | Sprint 3 | Agent assembles a context summary | To Do
CD-009 | B. Onboarding & KYC | As the system, I validate document type & file safety so that bad uploads are rejected | Backend | Validation, AV scan | Must | 4 | 3 | Sprint 2 | Wrong type/oversized/malicious file blocked | To Do
CD-011 | B. Onboarding & KYC | As an SME applicant, I can track my onboarding status so that I know what's pending | Mobile | React Native | Must | 4 | 3 | Sprint 2 | Status reflects stage; updates in near real-time | To Do
CD-018 | C. Case & Alert Mgmt | As a lead, I assign cases to analysts so that work is distributed | Web / Backend | Spring Boot | Must | 4 | 3 | Sprint 2 | Case owner set; visible in queue | To Do
CD-043 | E. Agentic AI Copilot | As an analyst, I can edit the agent draft before approving so that I stay in control | Web | React | Must | 4 | 3 | Sprint 3 | Draft is editable pre-approval | To Do
CD-049 | G. Analytics Dashboard | As a manager, I see risk-distribution charts so that I understand the portfolio | Data Viz | Chart.js | Must | 4 | 3 | Sprint 3 | Risk buckets charted | To Do
CD-060 | J. Admin & Master Data | As an admin, I manage users & roles so that access stays correct | Web / Admin | React, Spring Boot | Must | 4 | 3 | Sprint 2 | CRUD users & assign roles | To Do
CD-064 | K. DevSecOps & Cloud | As a team, services are containerised so that they deploy consistently | DevSecOps | Docker | Must | 4 | 3 | Sprint 1 | Images build & run locally/cloud | To Do
CD-066 | K. DevSecOps & Cloud | As a team, dependency & container scans run so that known vulns are caught | DevSecOps | Trivy, Dependabot | Must | 4 | 3 | Sprint 2 | Scan runs in pipeline; report produced | To Do
CD-067 | K. DevSecOps & Cloud | As a team, SAST/DAST security testing runs so that vulnerabilities are found & remediated | DevSecOps | Semgrep, OWASP ZAP | Must | 4 | 3 | Sprint 3 | Security report + remediation notes | To Do
CD-029 | D. Monitoring & ML | As a team, the model has a training & evaluation pipeline (P/R/F1/ROC-AUC) so that quality is measured | ML | scikit-learn, XGBoost | Must | 4 | 5 | Sprint 2 | Held-out metrics reported & documented | To Do
CD-068 | K. DevSecOps & Cloud | As a team, automated unit/integration/e2e tests run so that regressions are caught | DevSecOps | JUnit, pytest, Playwright | Must | 4 | 5 | Sprint 2 | Tests gate the pipeline | To Do
CD-012 | B. Onboarding & KYC | As the system, I screen applicants against sanctions/PEP lists so that high-risk parties are flagged | Backend / ML | List match / fuzzy match | Should | 5 | 5 | Sprint 2 | Name match raises alert with score | To Do
CD-003 | A. Auth & Access | As a user, I authenticate with MFA (OTP) so that accounts are harder to compromise | Backend / Mobile | TOTP / SMS OTP | Should | 4 | 3 | Sprint 2 | OTP required at login; time-limited code | To Do
CD-023 | C. Case & Alert Mgmt | As a lead, cases show SLA timers & ageing so that overdue work is visible | Backend / Web | Spring Boot | Should | 4 | 3 | Sprint 3 | Ageing highlighted; SLA breach flagged | To Do
CD-041 | E. Agentic AI Copilot | As an auditor, I see an agent run trace so that AI reasoning is transparent | Agentic AI / Backend | Trace log | Should | 4 | 3 | Sprint 3 | Each run stores steps/tools/inputs | To Do
CD-042 | E. Agentic AI Copilot | As a team, prompts have guardrails so that unsafe/irrelevant output is limited | Agentic AI | Guardrails | Should | 4 | 3 | Sprint 3 | Injection/out-of-scope handled | To Do
CD-054 | H. MLRO Mobile | As an MLRO, I see an approval inbox on mobile so that I can act anywhere | Mobile | React Native | Should | 4 | 3 | Sprint 3 | Pending approvals listed on mobile | To Do
CD-055 | H. MLRO Mobile | As an MLRO, I approve/escalate on mobile with the risk explanation so that decisions are informed | Mobile | React Native | Should | 4 | 3 | Sprint 3 | Approve/escalate updates case | To Do
CD-010 | B. Onboarding & KYC | As an analyst, KYC fields are auto-extracted (OCR) so that manual entry is reduced | ML / Backend | AWS Textract / Tesseract | Should | 4 | 5 | Sprint 2 | Name/ID/expiry parsed with confidence score | To Do
CD-036 | E. Agentic AI Copilot | As the agent, I retrieve related cases/customer profile as a tool so that context is complete | Agentic AI | RAG / DB tool | Should | 4 | 5 | Sprint 3 | Agent cites related records | To Do
CD-040 | E. Agentic AI Copilot | As the agent, I ground narratives via RAG over AML rules so that output is regulation-aligned | Agentic AI | Vector store, RAG | Should | 4 | 5 | Sprint 3 | Narrative references relevant rule | To Do
CD-004 | A. Auth & Access | As a user, I can reset my password so that I can recover access | Backend / Web | Email token | Should | 3 | 2 | Sprint 2 | Reset link expires; new password enforced | To Do
CD-005 | A. Auth & Access | As a user, my session auto-expires so that unattended sessions are safe | Backend | JWT expiry / refresh | Should | 3 | 2 | Sprint 2 | Idle timeout logs user out | To Do
CD-020 | C. Case & Alert Mgmt | As an analyst, I add notes/comments so that context is captured | Web | React | Should | 3 | 2 | Sprint 2 | Notes saved with author/time | To Do
CD-047 | F. STR Reporting | As a compliance lead, I see an STR register/log so that filings are tracked | Backend | Spring Boot | Should | 3 | 2 | Sprint 3 | All STRs listed with status/date | To Do
CD-058 | I. Audit & Privacy | As a user, I get email/in-app notifications so that I act on assignments | Backend | Spring Boot | Should | 3 | 2 | Sprint 3 | Assignment triggers notification | To Do
CD-069 | K. DevSecOps & Cloud | As a team, secrets are managed securely so that no credentials leak | DevSecOps | AWS Secrets Manager | Should | 3 | 2 | Sprint 3 | No secrets in code; pulled at runtime | To Do
CD-070 | K. DevSecOps & Cloud | As a developer, APIs are versioned & documented so that clients integrate reliably | Backend | OpenAPI / Swagger | Should | 3 | 2 | Sprint 2 | Swagger UI lists versioned endpoints | To Do
CD-022 | C. Case & Alert Mgmt | As an analyst, I search & filter cases so that I find items fast | Web | React | Should | 3 | 3 | Sprint 3 | Filter by status/risk/date/owner | To Do
CD-032 | D. Monitoring & ML | As an admin, I configure risk thresholds so that sensitivity is tunable | Backend / Admin | Spring Boot | Should | 3 | 3 | Sprint 3 | Threshold change affects alerting | To Do
CD-033 | D. Monitoring & ML | As the system, a batch scoring job runs so that backlogs are scored regularly | ML / Backend | Scheduler | Should | 3 | 3 | Sprint 3 | Scheduled job scores new transactions | To Do
CD-046 | F. STR Reporting | As an MLRO, I export the STR (PDF/structured) so that it can be filed | Backend | PDF generation | Should | 3 | 3 | Sprint 3 | Export produces formatted document | To Do
CD-050 | G. Analytics Dashboard | As a manager, I see SLA-breach & workload charts so that I balance the team | Data Viz | Chart.js | Should | 3 | 3 | Sprint 3 | Workload per analyst charted | To Do
CD-051 | G. Analytics Dashboard | As a manager, I see trends over time (alerts, STRs) so that I spot shifts | Data Viz | Chart.js | Should | 3 | 3 | Sprint 3 | Time-series charts render | To Do
CD-053 | G. Analytics Dashboard | As a manager, I export a compliance report so that reports are distinct from dashboards | Backend / Web | PDF/CSV | Should | 3 | 3 | Sprint 3 | Report exports as file | To Do
CD-056 | H. MLRO Mobile | As an MLRO, I receive push notifications for high-risk alerts so that I respond quickly | Mobile / Backend | FCM push | Should | 3 | 3 | Sprint 3 | High-risk alert triggers push | To Do
CD-059 | I. Audit & Privacy | As a DPO, PDPA data-retention & privacy controls apply so that personal data is handled lawfully | Backend | Retention policy | Should | 3 | 3 | Sprint 3 | Retention rules enforced | To Do
CD-061 | J. Admin & Master Data | As an admin, I configure risk rules so that policy is maintainable | Web / Admin | Spring Boot | Should | 3 | 3 | Sprint 3 | Rules editable via UI | To Do
CD-071 | K. DevSecOps & Cloud | As an operator, logging & monitoring exist so that issues are diagnosable | DevSecOps | CloudWatch | Should | 3 | 3 | Sprint 3 | Logs & basic alerts available | To Do
CD-006 | A. Auth & Access | As an admin, I can view login/audit events so that access is traceable | Backend | Audit table | Could | 3 | 2 | Sprint 3 | Login events recorded with user/time/IP | To Do
CD-015 | B. Onboarding & KYC | As the system, I remind on periodic re-KYC so that records stay current | Backend | Scheduler | Could | 3 | 2 | Sprint 3 | Reminder generated at review date | To Do
CD-014 | B. Onboarding & KYC | As an analyst, I can capture beneficial-ownership details so that UBO is known | Web / Mobile | Form, Spring Boot | Could | 3 | 3 | Sprint 3 | UBO records linked to customer | To Do
CD-031 | D. Monitoring & ML | As a team, model performance is monitored so that drift is detectable | ML | Metrics logging | Could | 3 | 3 | Sprint 3 | Metrics tracked over runs | To Do
CD-052 | G. Analytics Dashboard | As a manager, I drill down from a chart to underlying cases so that I investigate spikes | Web | React | Could | 3 | 3 | Sprint 3 | Chart click filters case list | To Do
CD-021 | C. Case & Alert Mgmt | As an analyst, I see duplicate/linked cases so that I avoid rework | ML / Backend | Vector / rule similarity | Could | 3 | 5 | Sprint 3 | Similar cases suggested on open | To Do
CD-013 | B. Onboarding & KYC | As an SME applicant, I can capture a declaration / e-signature so that consent is recorded | Mobile | React Native | Could | 2 | 3 | Sprint 3 | Signature stored & timestamped | To Do
CD-024 | C. Case & Alert Mgmt | As an analyst, I perform bulk actions on alerts so that low-risk noise clears quickly | Web | React | Could | 2 | 3 | Sprint 3 | Multi-select close/assign works | To Do
CD-062 | J. Admin & Master Data | As an admin, I manage reference data (sanctions/PEP list) so that screening stays current | Web / Admin | Spring Boot | Could | 2 | 3 | Sprint 3 | List uploadable/editable | To Do

## Sprint Plan & Summary
ComplyDesk — Prioritisation Summary
Feature COUNT by MoSCoW × Sprint
MoSCoW | Sprint 1 | Sprint 2 | Sprint 3 | Total
Must | 6 | 15 | 13 | 34
Should | 0 | 7 | 21 | 28
Could | 0 | 0 | 9 | 9
Total | 6 | 22 | 43 | 71
STORY POINTS by MoSCoW × Sprint
MoSCoW | Sprint 1 | Sprint 2 | Sprint 3 | Total
Must | 24 | 68 | 54 | 146
Should | 0 | 21 | 64 | 85
Could | 0 | 0 | 27 | 27
Total | 24 | 89 | 145 | 258

## Legend & Method
ComplyDesk — Backlog Legend & Prioritisation Method
Prioritisation method
MoSCoW | Must = MVP-critical (demo won't work without it); Should = important, not vital; Could = nice-to-have if time; Won't = out of scope this cycle
Ordering | Backlog is sorted by MoSCoW, then Business Value (desc), then Story Points (asc) — highest value / lowest effort first within each band
Business Value | 1 (low) to 5 (critical) — impact on the core demo & stakeholder value
Story Points | Relative effort (Fibonacci: 2,3,5,8) — not hours
Target Sprint | Sprint 1 = Design & Prototype; Sprint 2 = Development/UAT/CI-CD; Sprint 3 = Development/agent/dashboard/security
Pillar legend (maps to the 5 mandated technologies + backbone)
Mobile | React Native — SME onboarding app + MLRO approvals
Web | React — analyst/MLRO/admin workspace
ML | Python FastAPI + XGBoost + SHAP — transaction risk scoring & explainability
Agentic AI | LangGraph LLM agent with tools + human-in-the-loop — investigation copilot
Data Viz | Chart.js — compliance analytics dashboard
Backend | Java Spring Boot + PostgreSQL — common backend, workflow, audit
DevSecOps | GitHub Actions, Docker, AWS, Trivy/Semgrep/ZAP — CI/CD, cloud, security
MVP definition | All 'Must' items form the 4-week MVP. 'Should' pulled in if capacity allows; 'Could' only after Musts are stable.
Note | Runs entirely on synthetic AML data (AMLSim-style). No real bank integration. Agent actions are advisory & approval-gated (MAS FEAT-aligned).