## Product Backlog
WBGT CrewSafe SG — Prioritised Product Backlog
ID | Feature ID | Priority (MoSCoW) | Feature / User Story | Story Points | Implementation Technologies | Acceptance Summary | Sprint
US-19 | F-30 | Must | Prepare prioritised backlog, high-level use-case diagram and UI prototype screens | 5 | Design and documentation tooling (Figma / AI design tools); no runtime technology | Backlog, use-case diagram and navigable mockups accepted by advisor | 0
US-20 | F-31 | Must | Spike: confirm NEA WBGT / lightning feasibility and cache demo fixtures | 3 | Backend (Spring Boot), NEA data.gov.sg WBGT / lightning APIs, cached JSON fixtures | Live pull demonstrated; dated fixtures cached for offline demo | 0
US-01 | F-01 | Must | Authenticate and see only my assigned site | 5 | Amazon Cognito + JWT, Spring Security resource server, Web (React, TS), Mobile (React Native) | RBAC and negative authorization tests pass | 1
US-02 | F-02 | Must | Create a shift with workers, tasks and intensity | 8 | Web (React, MUI), Backend (Spring Boot, Spring Data JPA, PostgreSQL) | Shift validation and assignments persist | 1
US-03 | F-03 | Must | Worker views shift and submits readiness flags | 5 | Mobile (React Native, Expo), Backend (Spring Boot, PostgreSQL) | Only assigned worker can submit; no medical free text | 1
US-04 | F-04 | Must | Ingest and store WBGT / weather with freshness | 8 | Backend (Spring Boot scheduler), NEA data.gov.sg APIs, PostgreSQL | Live and fixture modes work; duplicate ingestion safe | 1
US-04L | F-05 | Must | Lightning stop-work warning shown above WBGT | 5 | Backend (Spring Boot), NEA lightning observation API, React + React Native | Risk state clear/advisory/stop-work; warning atop WBGT; overrides heat plan | 1
US-05 | F-06 | Must | Supervisor sees current conditions and active shift context | 5 | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | Web view uses shared backend and shows freshness | 1
US-21 | F-19 | Must | Provision cloud staging infrastructure and secrets management | 5 | Terraform with the HashiCorp AWS Provider: CloudFront/S3, ECS Fargate, ALB, ECR, RDS, Cognito, Bedrock, EventBridge Scheduler, Secrets Manager | Web + mobile reach one deployed backend; no secrets in source | 1
US-22 | F-20 | Must | Establish CI pipeline skeleton (build, unit tests, SAST, secret scan) | 5 | CI/CD pipeline: automated tests and application, dependency, secret, infrastructure and container scanning; build, test, scan, publish and deploy approved releases | PR triggers build, tests and scans; main branch protected | 1
US-23 | F-26 | Should | Baseline observability: health checks, correlation IDs, structured logs | 3 | Structured JSON logs, correlation IDs, health checks (Spring Boot Actuator), Amazon CloudWatch | Health endpoints live; correlation IDs traced end-to-end | 1
US-06 | F-07 | Must | System forecasts 30 / 60-minute WBGT | 8 | Python ML (pandas, scikit-learn; HistGradientBoostingRegressor primary, Ridge / persistence baselines, XGBoost optional challenger; time-based validation) | Baselines measured; versioned prediction returned | 2
US-07 | F-08 | Must | Evaluate the correct deterministic policy actions | 8 | Backend (Java 21 rules engine, PostgreSQL policy config) | Boundary and mixed-worker tests pass | 2
US-08 | F-09 | Must | Supervisor receives an explainable agent draft plan | 8 | Agentic AI (Python, FastAPI, LangChain / LangGraph, Amazon Bedrock, tool calling, Pydantic schemas) | No unsupported actions; policy / model references shown | 2
US-09 | F-10 | Must | Supervisor approves, edits or rejects a plan | 5 | Web (React), Backend (Spring Boot) | Draft and final versions retained; authorization enforced | 2
US-10 | F-11 | Must | Worker receives and acknowledges an approved action | 8 | Mobile (React Native), Backend (idempotency, PostgreSQL) | Only affected workers see it; idempotency works | 2
US-11 | F-12 | Must | Worker logs rest / hydration or raises a concern | 5 | Mobile (React Native), Backend (Spring Boot) | Status updates in supervisor view | 2
US-12 | F-13 | Must | Supervisor monitors pending, late and completed actions | 5 | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | Live state and alert count match backend records | 2
US-24 | F-22 | Must | Safety manager configures and versions the active heat policy | 5 | Web (React), Backend (Java 21, Spring Boot, Spring Data JPA), PostgreSQL policy_version tables | Versioned catalogue with source & effective date; recommendations cite version | 2
US-27 | F-20 | Must | Complete DevSecOps pipeline (dependency + container scan, auto staging deploy, smoke tests) | 5 | CI/CD pipeline: automated tests and application, dependency, secret, infrastructure and container scanning; build, test, scan, publish and deploy approved releases | Pipeline scans, deploys staging and runs smoke tests | 2
US-36 | F-21 | Should | Trace and evaluate agent runs in AI observability tooling | 3 | LangSmith (agent run tracing, plan-quality evaluation, tool-call monitoring, prompt testing; not the authoritative audit record) | Every agent run traced with tool calls and plan-quality score; traces linked to audit trace ID | 2
US-13 | F-14 | Must | Manager views compliance and response-time charts | 8 | Web (React, Chart.js), Backend aggregation | Metrics verified against seeded expected values | 3
US-14 | F-15 | Must | Manager views forecast accuracy and fallback status | 5 | Web (Chart.js), Python ML metrics (time-based validation), Backend | Metrics match evaluation artifact | 3
US-15 | F-16 | Must | Manager exports the audit timeline | 5 | Backend (export service), Web, PostgreSQL append-only audit | Export contains trace IDs, actors, rules and decisions | 3
US-16 | F-17 | Must | Safe degraded behaviour during dependency failure | 8 | Backend fallback adapters (NEA / ML / LLM) | NEA, ML and LLM failure scenarios pass | 3
US-17 | F-11 | Should | In-app reminder for an unacknowledged approved action | 3 | Mobile (React Native), Backend (idempotency, PostgreSQL) | Reminder cannot alter instruction | 3
US-25 | F-24 | Should | Show readiness-check freshness and missing checks | 3 | Mobile (React Native) + Web (React), Backend (Spring Boot), PostgreSQL | Stale or missing readiness flagged to supervisor | 3
US-26 | F-23 | Should | STPA-derived agent guardrail verification (allowlist + approval gate) | 5 | Agentic AI (LangGraph guardrails, Pydantic schemas), Backend validation (Java 21), automated test harness | Unsupported-action rate zero; approval-gate bypass blocked and audited | 3
US-28 | F-27 | Must | Security testing suite and remediation evidence | 8 | OWASP-style tests (authz, injection, XSS, prompt injection, audit tamper); CI/CD dependency, secret, infrastructure and container scanning | Findings, severity, remediation and re-test documented; no unresolved high/critical | 3
US-29 | F-25 | Should | ML model card with SHAP explainability and forecast reliability | 3 | Python ML (scikit-learn, SHAP), model-card documentation, time-based validation metrics | Card includes SHAP drivers, calibration and per-band error | 3
US-30 | F-29 | Should | Admin manages users, roles, sites and integrations | 5 | Web (React), Amazon Cognito, Spring Security, Backend (Spring Boot), PostgreSQL | Admin CRUD with RBAC; every change audited | 3
US-31 | F-28 | Should | Accessibility and performance checks (WCAG 2.1 AA basics; p95 latency) | 3 | Web (React) + Mobile (React Native), axe / Lighthouse, load testing (WCAG 2.1 AA basics; p95 latency) | WCAG AA basics met; read p95 <1s, write p95 <2s | 3
US-18 | F-18 | Could | Worker views an approved instruction in another language | 5 | Agentic AI (human-approved template via LangChain on Amazon Bedrock), Mobile | Human-approved template only | Stretch
US-32 | F-32 | Could | QR check-in at a simulated rest zone | 3 | Mobile (React Native, Expo Camera), Backend (Spring Boot), PostgreSQL append-only audit | Scan logs rest at zone; event audited | Stretch
US-33 | F-33 | Could | Multi-site management view | 5 | Web (React, Chart.js), Backend (Spring Boot), site-scoped RBAC | Manager switches and compares multiple sites | Stretch
US-34 | F-34 | Could | Supervisor-entered local WBGT reading with source & timestamp | 3 | Web (React) + Mobile (React Native), Backend (Spring Boot), PostgreSQL with source & timestamp | Manual reading stored with source/time; no station-equivalence claim | Stretch
US-35 | F-35 | Could | Push notifications via Firebase Cloud Messaging | 5 | Mobile (React Native, Expo + Firebase Cloud Messaging), Backend (Spring Boot) | Approved action pushes to worker device | Stretch

## Features
Features — Proposed Features & Implementation Technologies
Feature ID | Feature (use case / user story) | Additional Details (Implementation Technologies) | Backlog Stories
F-01 | Authenticate & site-scoped access | Amazon Cognito + JWT, Spring Security resource server, Web (React, TS), Mobile (React Native) | US-01
F-02 | Configure shift, tasks & assignments | Web (React, MUI), Backend (Spring Boot, Spring Data JPA, PostgreSQL) | US-02
F-03 | Complete worker readiness check | Mobile (React Native, Expo), Backend (Spring Boot, PostgreSQL) | US-03
F-04 | Ingest WBGT & weather with freshness | Backend (Spring Boot scheduler), NEA data.gov.sg APIs, PostgreSQL | US-04
F-05 | Lightning warning above WBGT (stop-work) | Backend (Spring Boot), NEA lightning observation API, React + React Native | US-04L
F-06 | View current & forecast risk (live conditions) | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | US-05
F-07 | Forecast 30 / 60-minute WBGT | Python ML (pandas, scikit-learn; HistGradientBoostingRegressor primary, Ridge / persistence baselines, XGBoost optional challenger; time-based validation) | US-06
F-08 | Evaluate deterministic heat policy | Backend (Java 21 rules engine, PostgreSQL policy config) | US-07
F-09 | Generate explainable agent draft plan | Agentic AI (Python, FastAPI, LangChain / LangGraph, Amazon Bedrock, tool calling, Pydantic schemas) | US-08
F-10 | Approve / edit / reject plan | Web (React), Backend (Spring Boot) | US-09
F-11 | Dispatch & acknowledge worker action | Mobile (React Native), Backend (idempotency, PostgreSQL) | US-10, US-17
F-12 | Log rest / hydration & raise safety concern | Mobile (React Native), Backend (Spring Boot) | US-11
F-13 | Monitor completion (live status board) | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | US-12
F-14 | Compliance & response-time dashboard | Web (React, Chart.js), Backend aggregation | US-13
F-15 | Model-performance dashboard | Web (Chart.js), Python ML metrics (time-based validation), Backend | US-14
F-16 | Export audit timeline (CSV / PDF) | Backend (export service), Web, PostgreSQL append-only audit | US-15
F-17 | Graceful degraded mode | Backend fallback adapters (NEA / ML / LLM) | US-16
F-18 | [Stretch] Multilingual instruction template | Agentic AI (human-approved template via LangChain on Amazon Bedrock), Mobile | US-18
F-19 | [Cross-cutting] Cloud deployment | Terraform with the HashiCorp AWS Provider: CloudFront/S3, ECS Fargate, ALB, ECR, RDS, Cognito, Bedrock, EventBridge Scheduler, Secrets Manager | US-21
F-20 | [Cross-cutting] DevSecOps pipeline | CI/CD pipeline: automated tests and application, dependency, secret, infrastructure and container scanning; build, test, scan, publish and deploy approved releases | US-22, US-27
F-21 | [Cross-cutting] AI observability | LangSmith (agent run tracing, plan-quality evaluation, tool-call monitoring, prompt testing; not the authoritative audit record) | US-36
F-22 | Configure & version heat policy | Web (React), Backend (Java 21, Spring Boot, Spring Data JPA), PostgreSQL policy_version tables | US-24
F-23 | Agent guardrail verification (STPA, allowlist, approval gate) | Agentic AI (LangGraph guardrails, Pydantic schemas), Backend validation (Java 21), automated test harness | US-26
F-24 | Readiness-check freshness & missing-check indicators | Mobile (React Native) + Web (React), Backend (Spring Boot), PostgreSQL | US-25
F-25 | ML model card (SHAP explainability & reliability) | Python ML (scikit-learn, SHAP), model-card documentation, time-based validation metrics | US-29
F-26 | [Cross-cutting] Observability & health monitoring | Structured JSON logs, correlation IDs, health checks (Spring Boot Actuator), Amazon CloudWatch | US-23
F-27 | [Cross-cutting] Security testing & remediation evidence | OWASP-style tests (authz, injection, XSS, prompt injection, audit tamper); CI/CD dependency, secret, infrastructure and container scanning | US-28
F-28 | [Cross-cutting] Accessibility & performance | Web (React) + Mobile (React Native), axe / Lighthouse, load testing (WCAG 2.1 AA basics; p95 latency) | US-31
F-29 | Admin: users, roles, sites & integrations | Web (React), Amazon Cognito, Spring Security, Backend (Spring Boot), PostgreSQL | US-30
F-30 | [Inception] Prioritised backlog, use-case diagram & UI prototype | Design and documentation tooling (Figma / AI design tools); no runtime technology | US-19
F-31 | [Spike] NEA feed feasibility & cached demo fixtures | Backend (Spring Boot), NEA data.gov.sg WBGT / lightning APIs, cached JSON fixtures | US-20
F-32 | [Stretch] QR rest-zone check-in | Mobile (React Native, Expo Camera), Backend (Spring Boot), PostgreSQL append-only audit | US-32
F-33 | [Stretch] Multi-site management view | Web (React, Chart.js), Backend (Spring Boot), site-scoped RBAC | US-33
F-34 | [Stretch] Supervisor-entered local WBGT reading | Web (React) + Mobile (React Native), Backend (Spring Boot), PostgreSQL with source & timestamp | US-34
F-35 | [Stretch] Push notifications | Mobile (React Native, Expo + Firebase Cloud Messaging), Backend (Spring Boot) | US-35

## Business Process
Business Process — Heat-Safety Operations Workflow
Actor | Features
Core observe → decide → approve → dispatch → acknowledge → audit loop
NEA Weather Service | Ingest WBGT, weather & lightning (system-triggered)
System (Lightning) | Classify lightning risk; raise stop-work warning above WBGT
System (ML) | Forecast 30 / 60-minute WBGT
System (Policy) | Evaluate deterministic heat policy
System (Agent) | Draft explainable intervention plan
Site Supervisor | Review & approve / edit / reject plan
Site Supervisor | Configure shift & tasks
Site Supervisor | Monitor current & forecast risk
Site Supervisor | Monitor completion & send approved reminder
Site Supervisor | Review readiness freshness & missing checks
Site Supervisor | Enter a local WBGT reading with source & timestamp [Stretch]
Outdoor Worker | Receive lightning stop-work alert & seek shelter
Outdoor Worker | Complete readiness check
Outdoor Worker | Receive & acknowledge action
Outdoor Worker | Log rest / hydration
Outdoor Worker | Raise safety concern
Outdoor Worker | Receive a push notification for an approved action [Stretch]
Outdoor Worker | Check in at a rest zone by QR scan [Stretch]
Outdoor Worker | View an approved instruction in another language [Stretch]
Oversight & governance
Safety Manager | Configure & version the active heat policy (source & effective date)
Safety Manager | View dashboards & audit / export timeline
Safety Manager | Review agent guardrail & security-testing evidence
Safety Manager | Review ML model card & forecast reliability
Site Manager | Compare performance across multiple sites [Stretch]
Administrator | Manage users, roles, sites & integrations

## Technologies
Architecture-Centric Features — Technology Stack
Layer | Technology | Purpose in WBGT CrewSafe SG
Web app | React, TypeScript, Vite, Material UI, Chart.js | Supervisor / manager / admin console, dashboards, approval workflow
Mobile app | React Native, Expo, TypeScript | Worker readiness, instructions, acknowledgement, rest / hydration logs
Identity | Amazon Cognito, JWT, Spring Security resource server | Sign-in, role claims and site-scoped access for web and mobile
Shared backend | Java 21, Spring Boot, Spring Security, Spring Data JPA | System of record, RBAC, policy engine host, audit
Machine learning | Python, pandas, scikit-learn; persistence and Ridge baselines; HistGradientBoostingRegressor primary; optional XGBoost challenger | Train and run direct 30- and 60-minute WBGT forecasts using time-based validation
Agentic AI | Python, FastAPI, LangChain, LangGraph, Amazon Bedrock, tool calling, Pydantic schemas | Use an approved foundation model to invoke guarded tools and produce validated draft plans
AI observability | LangSmith | Trace agent runs, evaluate plan quality and monitor tool calls; not the authoritative audit record
Database | PostgreSQL, migration-managed schema, protected append-only audit events | Users, sites, shifts, observations, recommendations, append-only audit
Realtime | Server-Sent Events (supervisor), refresh / polling on mobile | Live condition, plan and acknowledgement updates
API contract | OpenAPI 3, REST /api/v1, generated TypeScript clients | Contract between clients and shared backend
Cloud | AWS CloudFront/S3, ECS Fargate, ALB, ECR, RDS, Cognito, Bedrock, EventBridge Scheduler, Secrets Manager | Host web, containers, database, identity, model inference, scheduled forecasts and secrets
Infrastructure as code | Terraform with the HashiCorp AWS Provider | Reproducible AWS provisioning through CI/CD
Observability | Structured JSON logs, correlation IDs, health checks, Amazon CloudWatch | Health checks, traceability, integration-failure metrics
DevSecOps | CI/CD, automated tests and application, dependency, secret, infrastructure and container scanning | Build, test, scan, publish and deploy approved releases

## Project Status
Project Status Report (C = Completed · I = In Progress · blank = Not started)
Feature | Implementation Technologies | Sprint | Requirements | Development | Integration Testing | Deployed to Cloud
[Inception] Prioritised backlog, use-case diagram & UI prototype | Design and documentation tooling (Figma / AI design tools); no runtime technology | 0
[Spike] NEA feed feasibility & cached demo fixtures | Backend (Spring Boot), NEA data.gov.sg WBGT / lightning APIs, cached JSON fixtures | 0
Authenticate & site-scoped access | Amazon Cognito + JWT, Spring Security resource server, Web (React, TS), Mobile (React Native) | 1
Configure shift, tasks & assignments | Web (React, MUI), Backend (Spring Boot, Spring Data JPA, PostgreSQL) | 1
Complete worker readiness check | Mobile (React Native, Expo), Backend (Spring Boot, PostgreSQL) | 1
Ingest WBGT & weather with freshness | Backend (Spring Boot scheduler), NEA data.gov.sg APIs, PostgreSQL | 1
Lightning warning above WBGT (stop-work) | Backend (Spring Boot), NEA lightning observation API, React + React Native | 1
View current & forecast risk (live conditions) | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | 1
[Cross-cutting] Cloud deployment | Terraform with the HashiCorp AWS Provider: CloudFront/S3, ECS Fargate, ALB, ECR, RDS, Cognito, Bedrock, EventBridge Scheduler, Secrets Manager | 1
[Cross-cutting] DevSecOps pipeline | CI/CD pipeline: automated tests and application, dependency, secret, infrastructure and container scanning; build, test, scan, publish and deploy approved releases | 1
[Cross-cutting] Observability & health monitoring | Structured JSON logs, correlation IDs, health checks (Spring Boot Actuator), Amazon CloudWatch | 1
Forecast 30 / 60-minute WBGT | Python ML (pandas, scikit-learn; HistGradientBoostingRegressor primary, Ridge / persistence baselines, XGBoost optional challenger; time-based validation) | 2
Evaluate deterministic heat policy | Backend (Java 21 rules engine, PostgreSQL policy config) | 2
Generate explainable agent draft plan | Agentic AI (Python, FastAPI, LangChain / LangGraph, Amazon Bedrock, tool calling, Pydantic schemas) | 2
Approve / edit / reject plan | Web (React), Backend (Spring Boot) | 2
Dispatch & acknowledge worker action | Mobile (React Native), Backend (idempotency, PostgreSQL) | 2
Log rest / hydration & raise safety concern | Mobile (React Native), Backend (Spring Boot) | 2
Monitor completion (live status board) | Web (React, Chart.js), Server-Sent Events, Backend (Spring Boot) | 2
Configure & version heat policy | Web (React), Backend (Java 21, Spring Boot, Spring Data JPA), PostgreSQL policy_version tables | 2
[Cross-cutting] AI observability | LangSmith (agent run tracing, plan-quality evaluation, tool-call monitoring, prompt testing; not the authoritative audit record) | 2
Compliance & response-time dashboard | Web (React, Chart.js), Backend aggregation | 3
Model-performance dashboard | Web (Chart.js), Python ML metrics (time-based validation), Backend | 3
Export audit timeline (CSV / PDF) | Backend (export service), Web, PostgreSQL append-only audit | 3
Graceful degraded mode | Backend fallback adapters (NEA / ML / LLM) | 3
Agent guardrail verification (STPA, allowlist, approval gate) | Agentic AI (LangGraph guardrails, Pydantic schemas), Backend validation (Java 21), automated test harness | 3
Readiness-check freshness & missing-check indicators | Mobile (React Native) + Web (React), Backend (Spring Boot), PostgreSQL | 3
ML model card (SHAP explainability & reliability) | Python ML (scikit-learn, SHAP), model-card documentation, time-based validation metrics | 3
[Cross-cutting] Security testing & remediation evidence | OWASP-style tests (authz, injection, XSS, prompt injection, audit tamper); CI/CD dependency, secret, infrastructure and container scanning | 3
[Cross-cutting] Accessibility & performance | Web (React) + Mobile (React Native), axe / Lighthouse, load testing (WCAG 2.1 AA basics; p95 latency) | 3
Admin: users, roles, sites & integrations | Web (React), Amazon Cognito, Spring Security, Backend (Spring Boot), PostgreSQL | 3
[Stretch] Multilingual instruction template | Agentic AI (human-approved template via LangChain on Amazon Bedrock), Mobile | Stretch
[Stretch] QR rest-zone check-in | Mobile (React Native, Expo Camera), Backend (Spring Boot), PostgreSQL append-only audit | Stretch
[Stretch] Multi-site management view | Web (React, Chart.js), Backend (Spring Boot), site-scoped RBAC | Stretch
[Stretch] Supervisor-entered local WBGT reading | Web (React) + Mobile (React Native), Backend (Spring Boot), PostgreSQL with source & timestamp | Stretch
[Stretch] Push notifications | Mobile (React Native, Expo + Firebase Cloud Messaging), Backend (Spring Boot) | Stretch